* **100 Days Plan Key Dates:**
  + 2 Jun                     REQUEST FOR VARIANCE – 607 AOC/OSD submitted AIMC software/cloud stack request for variance (RFV)
  + 8 Aug 2024         START OF CONTRACT/AWARD – contract is approved, funds obligated
  + 14 Aug                  TASKORD – published
  + 14 Aug                  SOFA REQUEST FOR CONTRACT – Contracting Officer Submits SOFA designation for contract vehicle to USFK/FKAQ
  + 8 Aug                    HARDWARE PURCHASE – Palantir starts Procurement and Configuration
  + 16 Aug                  OBSERVERS – Palantir 3x Integrators arrive to observe UFS 24 Kill Chain execution
  + 19 – 29 Aug        UFS 24
  + 29 Aug                  SOFA APPROVED FOR CONTRACT – USFK/FKAQ approves SOFA designation for contract vehicle
  + 30 Aug                  SOFA REQUEST FOR CONTRACTORS – SOFA RO submits SOFA designation package for all Palantir Individual Contractors to USFK/FKAQ
  + 13 Sep                  SOFA APPROVED FOR CONTRACTORS – a USFK/FKAQ approves SOFA designation for Palantir contractors
  + 16 Sep                  EXECUTE SOW – Palantir Contractors execute contract Statement of Work (SOW) tasks
  + 17 Sep                  KICKOFF IPR (3-Star) – Palantir and 607 AOC Project Leads brief 7 AF/CC on project POA&M
  + 20 Sep                  COMBINED USER TEAM LEADS STANDUP – 607 AOC/AFOC stands up weekly, Combined User WG for Team Leads (Palantir Integrators/Combat Ops, ISR-T Project Leads) to plan User training/engagement actions
  + 22 Sep                  HARDWARE SHIPPING – Palantir sends AIMC platform to Osan AB
  + 29 Sep                  HARDWARE INSTALL – Palantir engineers access ACE network to install AIMC software/cloud stack on weapon system
  + 3 Oct                    AUTHORITY TO OPERATE – ACC AOC WS Systems Program Office approves AIMC platform variance and issues ATO
  + 8 Oct                    O-6 IPR – Palantir and 607 AOC Project Leads brief project status
  + 13 Oct                  AIMC IOC – Palantir engineers access integrate AIMC software into weapons system applications and data services/feeds
  + 14 Oct                  COMBINED DTC/TDC STANDUP – 607 AOC/AFOC stands up daily combined User Teams with Palantir Integrators providing training
  + 18 Oct                  COMBNED USER WG – starts weekly meetings with Palantir, Project manager, Project Team Leads, and Users
  + 7 Aug 2025         END OF CONTRACT